## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Planning
PROJECT PLAN
PROJECT NAME | Insights of Successful Students
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Comprehensive Analysis Report, Data Visualization, and Recommendations.
PROJECT SCOPE | Comprehensive Analysis Report, Data Visualization, and Recommendations.
PROJECT START DATE | 2023-08-05
PROJECT END DATE | 2023-08-30
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE
1 Initiation
| 1.1 Identify business problem |  | 2023-08-05
| 1.2 Understanding requirement |  | 2023-08-06
| 1.3 Create a project charter |  | 2023-08-07
| 1.4 Requirement gathering |  | 2023-08-07
2 Planning
| 2.1 Approval of business process |  | 2023-08-08
| 2.2 Baseline project plan |  | 2023-08-08
| 2.3 Team roles and responsibilities |  | 2023-08-09
3 Execution
| 3.1 Finalize design |  | 2023-08-10
| 3.2 Build |  | 2023-08-10
| 3.3 Gathering data from various sources |  | 2023-08-10
| 3.3.1 Data Cleaning remove the duplicates from data |  | 2023-08-11
| 3.3.2 then data transform |  | 2023-08-12
| 3.3.3 data preprocessing |  | 2023-08-13
| 3.3.4 data load with help of python or other tools |  | 2023-08-15
| 3.3.5 perform the operations on our data set |  | 2023-08-17
| 3.3.6 Create meaningful insights or dassboard |  | 2023-08-20
| 3.3.7 Create the report for stackholders and mangers |  | 2023-08-22
4 Testing
| 4.1 Manual Testing |  | 2023-08-25
| 4.2 automated testing |  | 2023-08-26
5 Deployment
| 5.1 Deployment |  | 2023-08-29
6 Closing
| 6.1 close the project |  | 2023-08-30